## Slide 1: PDF Uploader on Ariba Network <Supplier Name> with Arla Foods amba
Partner logo
Speaker’s Name, SAP
Month 00, 2022

## Slide 2: Agenda
PDF Supplier Integration
  How Can Suppliers Connect to the Ariba Network?
  PDF process flow
Current status/Scope
  Current status
  Project scope
  PDF Invoice Data positioning and specifics
  PDF Invoice step by step mapping process
  PDF Invoice Layout mapping
  PDF Invoice sample missing data or customizations
  PDF Supplier Onboarding
PDF Supplier Integration Specifics
  PDF Invoice Limitations
  PDF Invoice Sample
  Layout
  Current status/Business scope
  Project Scope and Details

## Slide 3: PDF Supplier integration

## Slide 4: How Can Suppliers Connect to the Ariba Network?
Ariba Network
SAP Ariba Cloud Integration Gateway
Suppliers
Buyer
EDI, EDIFACT, OAGIS, PIDX
cXML,
Portal / POFlip
CSV / PDF invoice

## Slide 5: PDF process flow
Invoice PDF
PDF Supplier
E-mail
Upload
Data Extraction
Optional bypass to auto-issue the invoice without further review
sig cXML
PDF attached

## Slide 6: Current Status/ Scope

## Slide 7
Tasks completed to date
PID (Project Initiation Document) delivered and reviewed by supplier?
Relationship accepted
Y/N
Location
Country
ANIDs
Buyer - <AN01014707685(-T)>
Ariba Network Accounts Configured
Y/N
Supplier - <AN00..>
Current Status

## Slide 8
Project Scope
How invoices are sent currently?
Procurement Solution
Type of Items in Scope
Email/Legacy integration
Procurement solution
Catalog
Non-catalog
Test Plan:
Invoice Types Supported | Invoice Types Not Supported
Individual Detail Invoice: applies against single PO referencing line items; line items should be material items. | Header Credit Memo (only for end of year adjustments) To be discussed on individual bases.
Partial invoice: Invoice against a portion of the items on a PO. | Invoice against PCard not allowed
Duplicate Invoice: invoice numbers cannot be reused in case of reject/cancel of original invoice | Information only invoice
lineLevelCreditMemo (cXML 1.2.018 and higher) invoice purpose set to “lineLevelCreditMemo” | Header Invoice: single invoice applying to single PO without item details
Non-PO Invoice: invoice against PO not transacted via the Ariba Network | Invoice against mixed PO
 | Consolidated invoices for goods or services: applies against multiple POs referencing line items; line items may be material items or service items.
 | Debit Memo
 | Service invoice

## Slide 9: PDF Invoice Data positioning and Specifics

## Slide 10: PDF Invoice step by step mapping process
Create an invoice sample where the positioning of all references extracted for conversion is shown; This invoice with circled references for extraction will help Cloud Trade to create more accurate mapping for your company;
Define invoices
Review all possible invoice layouts that are in use in the company (such as multi lines PDF, credit note, multi pages PDF, zero tax rate, invoice with charges, invoice to different Bill To/Ship To locations etc. ); Prepare for onboarding various cases: credit memo, invoice on one page, on many pages, different tax rates, multi tax rates, invoice with charges etc.; 48 hours are needed to create the initial custom mapping;
Invoice layout
Go to prod account Company Settings – Electronic Invoice Routing – PDF Invoice; Convert slide 11 into a PDF file and name it same as the name of the PDF file representing the invoice; upload the circled layout and the invoice used for layout creation, add up to 8 other invoices and start onboarding on your prod account. PDF Invoice tab will appear on test account once the company onboarded, note that from that tab the solution can be configured, for example drafts enabled/disabled, notification emails for drafts or failed invoices, whitelist sender email to send PDF invoices via email to Ariba Network etc.;
Onboarding
Testing
PDF/Mapping updates
Go - live
Use slide 11 from this presentation to insert your PDF invoice as a background picture and link all boxes with the associated reference on the invoice. This is kind of a mapping that will be used by Cloud Trade to understand where the data is positioned on your file and how it is labelled, so their tool can find and extract it. All those boxes represent the references that will be extracted from the PDF file. if missing data on the PDF file, there are few customization proposed by Cloud Trade, check slide 12;
Once initial mapping is created and account is onboarded for PDF Uploader, request buyer to create test PO (if PO-based invoices are in scope) and switch to test account; configure it in a way that you would like to use the functionality from PDF Invoice tab. Resend from test account all invoices used for onboarding and add additional cases if needed;
Once solution is tested and confirmed as running for all possible invoices cases on seller/buyer end, switch to prod, configure the PDF Invoice tab and use your Ariba account to send PDF Invoices;
If failed invoices, or invoices on conversion failed/pending, check the reason for the failure under Outbox – PDF Conversions or/and Invoice tab, if needed update the PDF layout in a way to meet buyer requirements in regards of e – invoicing (in case mandatory data for extraction is missing, for example the purchase order) and resend it. If PDF layout is accurate but the converted invoice contains errors, request mapping update on Cloud Trade by contacting your SIS or your buyer.

## Slide 11
Layout <Supplier Name> vs Arla Foods amba
1- Invoice Number
2- Invoice Date
1- InvoiceID
6- OrderID N (Purchase order)
7 – Tax Point date = Invoice date
8 – Supplier VAT ID
9 – From/Supplier Name
11 – From Supplier Street
13 – From Supplier City
15 – From Supplier Postcode
22 – Supplier Commercial Identifier
23 – Buyer VAT ID
24 – Sold To/ Customer Name
26 – Sold To/ Customer Street
28 – Sold To/Customer City
30 – Sold To/ Customer PostalCode
31 – Sold To/ Customer Country Code
34 – Bill To Name
36 – Bill To Street
38 – Bill To City
40 – Bill To Postcode
41 – Bill To Country Code
44 – Ship To Party
46 – Ship To Street
48 – Ship To City
50 – Ship To Postcode
51 – Ship To Country Code
54 – Ship From Name
55 – Ship From
56 – Ship From Street
58 – Ship From City
60 – Ship From PostalCode
61 – Ship From Country Code
69 – Gross Amount
70 – Net Amount
71 – Tax Amount
72 – Due Amount
73 – Subtotal Amount
74 – Currency
75 – Quantity
76 – Unit of Measure
77 – Unit price
78 – Line Number (on PO)
79 – Supplier Part ID
80 – Description
81 – Net Amount
82 – Tax Amount
83 – percentage rate
84 – category (VAT or other)
85 – Gross Amount
207 – Pay in Number of Days (default)
208 – Pay in Number of Days (dscount)
210 – tax Exchange Rate
213 – Comments
214 – TotalAmountWithoutTax
215 – alternate Amount
221 – SupplierPartAuxiliaryID
SIS Agree with supplier/buyer for the positioning of the data on the file, its labelling. Ask supplier to create the invoice layout and send it to CT during onboarding, emphasize the importance of that step already described on slide 10. Green – optional, orange – conversion will fail if missing
Custom – Requestor must be present if PO ID is missing
3- InvoiceID (original invoice in case of credit memo )
2 – Invoice date
Custom - Exempt detail/ZeroRated based on tax percentage field
0% - ZeroRated
0.00 % - exemptDetail

## Slide 12
PDF Invoice Sample – Missing data or customizations
All boxes from slide 11 should be linked to circled reference from your invoice. If some of the boxes are left unlinked, there could be missing data on the invoice, and the conversion will fail. To avoid invoice layout update in case it is not possible, Cloud Trade propose few customizations for sellers available listed on PID, tab named customizations. Here a link to all enhancements and customizations: Cloud Trade enhancements and customizations
Please mention here below all customizations/specific mapping requests that need to be implemented for seller, so conversion can be successful:
Inclusion service for Buyer ANID in the subject line of the mail
PO Line number
Unit of measure conversion (for example, supplier send Stück on invoice, but in cXML it needs to be converted into EA to match the PO unit of measure)
Single line invoice
Allowance and Charges
Header Level Freight – to be captured as additional line to the invoice
SIS Agree with supplier/buyer for any missing data on mapping customizations. Bear in mind that some of those are paid, check list
PID:

## Slide 13
Supplier Onboarding – Feature Activation
Note: you can only start onboarding from your Production account

## Slide 14
Invoice requirements Arla Foods amba | Can supplier meet the requirement?
Non-PO based invoices are allowed. If PO is missing, requestor name/initials should be always present on the invoice. | 
Quantity/line item price must be greater than 0. | 
Line level credit memo is supported for quantity/price adjustment. Invoice in reference of the credit memo is mandatory, | 
Duplicate invoice is allowed in case of cancelled, rejected and failed status of original invoice. | 
Past calendar year invoice numbers can be reused. | 
Currency cannot be changed and should match the PO currency. | 
Non-exiting lines on the PO can be added to PO-based invoices. | 
Invoice Sold To Name and Country code should match PO Bill To Name ad country. | 
Item descriptions are required – there is a system limitation of 40 characters per line item (long descriptions to be added as ‘comments’). | 
Suppliers are allowed to create tax rate and type for invoices. | 
Tax information is required on invoices. | 
Suppliers should provide order information or requester name. | 
Required addresses: Bill To, Sold To and Remit to. | 
Payment terms are required on PO based invoices and must match PO value. If non-PO based invoice, payment terms can be omitted. | 
Supplier VAT ID is required. | 
Tax amounts are required in local currency. | 
Explanation for zero rate VAT Is required. In case of zero rated invoice, tax rate must be 0% and exemptDetail = "zeroRated“. In case of exempt VAT, then tax rate must be 0.00% and exemptDetail = “exempt“. | 
SIs: Agree with supplier/buyer that they can meet the requirements

## Slide 15
PDF Invoice Limitations summary
Supported languages and countries in scope – please review general information about PDF invoicing on SAP Ariba?
One PDF file = One Invoice
When you e-mail your PDF invoice DO NOT Digitally sign emails, DO NOT enter other recipient then pdfinvoice-prod@ansmtp.ariba.com and email body should be in well formatted html. While whitelisting the email from which invoice will be sent, bear in mind that the matching is case sensitive
Draft invoice – in an initial phase of the project it can be recommended to activate the draft so that you get a chance to validate the accuracy of the invoice built on the basis of your PDF sample. However as the draft is overwriting the cXML sent from Cloud Trade pulling data from the supplier profile on AN, for testing it is recommended to be switched-off and retest it with drafts on to validate profile information. Please note that drafts are available just 50 days after last update.
Support for Application generated PDFs only (scanned PDFs supported through ICS).
Currently limited to Material invoices; Services invoices are currently out of scope. Summary invoices are out of scope.
PSS will support Enterprise suppliers post go live but it is not mandatory for PSS to support as PDF Invoicing can be a self-service solution for suppliers
REDO Mapping: The PDF samples are defined and final one the testing phase is signed-off. You should not change the layout of your samples after this phase because this might cause issues during data extractions and can lead to a re-do mapping
Customizations are available for free or for charge, please see link on page Slide 12

## Slide 16: Project Planning

## Slide 17: Seller Integration Methodology – Six stage integration according to our best practice
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Plan |  |  |  |  |  |  | 
 | Design |  |  |  |  |  | 
 |  | Build | Iteration - Testing Build & Corrections |  |  |  | 
 |  |  |  |  |  | Deploy | 
 |  |  |  |  |  |  | Go Live
Planning and Testing are the most critical and time consuming steps
Milestone dates to be determined at kick-off meeting
Plan
Build
Test
Design
Deploy
Go Live

## Slide 18: Project Life Cycle – Integration
Plan
Build
Test
Design
Deploy
Go Live
Kick Off Meeting Define Project Scope Documents, business rules, format | Configurations Confirm AN Account (ANID) set up Test account configured Successful onboarding | Supplier Development Performs Dev and QA testing of maps | UAT Testing Conduct UAT testing with Customer Pre-defined test scenarios | Migration to Production | Production Transactions Confirm successful transactions in Prod
Define Project Plan Agree on milestone dates. Create and agree on PDF layout with all mandatory extracted data circled and referenced | Confirm Relationship established in Test. Define test plan, identify test scenarios | Adjust PDF samples to meet buyer requirements if needed. Adjust mapping so the invoice can pass through AN. Deactivate the Draft Option for test environment. | Validate a final PDF sample per test scenario that meets requirements. Mapping updates might be necessary on Cloud Trade end. | Confirm AN Accounts configured in Production Confirm relationship established in Production | Support SI Post-production support
Commit to target Go Live date Define Project Team and Resources Contacts list and governance model. | Onboard with a good selection of sample invoices – we recommend at least 8 samples as well as the referenced PDF layout with all mandatory extracted data (cf page 11) | Submit PDF sample invoices to AN/Email for validation | Formal sign-off and acceptance | Buyer/Seller change management steps Communications, internal set ups | Ongoing technical support Project close

## Slide 19: Best practices for the supplier
Participate on weekly project follow up meetings (30 Minutes) with Supplier Integrator during the whole integration process;
    NB: When catalog in scope, the supplier must agree on a way to monitor the implementation with their CKE (mail, weekly meeting)
Plan
Get familiar with the PID, define roles and responsibilities of project resources and agree on milestone dates; carefully check which data is legal or busines requirement
Design
Defines the test scenarios; finalize successful onboarding in production using mapped supplier template and in test mode;
Build
Adjust invoices to include the buyer fields and label them correctly (Invoice Date, Order Number); Be prepared to correct the first couple of invoices in the Ariba Network (Draft invoices)
Test
Deploy
Go Live
Technical contact is engaged in day to day testing activities: post documents on Ariba test environment according to the test scenario, log on Ariba and check their status, correct Drafts and receive technical advices from Supplier Integrator;
NB: when catalog is scope, the catalog needs to be available before testing phase start
Supplier should migrate his account to production mode; internal communication for the switch to production mode is needed;
Document exchange runs in production mode; Supplier integrator provides technical support during the first two weeks;

## Slide 20: Timeline Milestones – will be reviewed and feedback on <Date>
Phase | Milestone | Owner | Duration | Date Due
Plan | Signoff on Project Plan & Timelines | Supplier | 1 weeks | 
Design | Buyer specs reviewed | Supplier | 1 weeks | 
Build | Data mapping completed | Supplier | 2 weeks | 
Test | Testing completed/Sign off on Test Cases | All | 3 weeks | 
Deploy | Confirm Cutover activities completed | All | 1 week | 
Go Live | Confirm Go Live (week 8) | All |  | 

## Slide 21: Roles & Responsibilities – Project Team Challenges and Governance

## Slide 22
Roles & Responsibilities – Project Team
Contact Name | Supplier Role | Responsibility
 | Project Lead (Operational Lead) | Main contact for project coordination Provide commitment to project timeline Understand buyer's transaction validation rules Participate in status meetings
 | Technical (Developer) | Provide technical details for integration to back-end systems Perform data mapping Assist in troubleshooting document failures Coordinate go live with functional resource
 | Testing Contact | Define & Validate catalogue content with buyer Analyze incoming Orders Generate Test Invoice Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Buyer Role | Responsibility
 | Project Lead (Supplier Enablement lead) | Main contact for project coordination Enforce compliance of project timelines
 | Technical (Developer) | Support of cXML/EDI Identified Supplier testing Provide connection parameters to ERP systems Assist in troubleshooting document errors from the application/ERP
 | Testing Contact | Define & Validate catalogue content with Supplier Generate Test Orders Reconcile and approve invoices Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Ariba Role | Responsibility
 | Seller Integrator | Manage end-to-end supplier integration Troubleshoot failed/rejected documents Ensure timely completion of project milestones Escalate issues to appropriate person/team
 | Supplier Enablement Lead | Consolidate all suppliers enablement status for reporting to <Customer Name>
 | Catalogue integrator | Support Setup and testing of Catalogue with buyer and supplier

## Slide 23: Challenges: Impacting Timeline
3rd Party Involvement
Y/N
In case of Y – specify relationship and details
System Maintenance
Dates/ Occurrences
Ex. every Sunday..
Vacation and Holiday Planning
<Supplier-Name of resource: list of holiday dates>
<Buyer-Name of resource: list of holiday dates>
<Ariba-Name of resource: list of holiday dates>
Y: Cloud Trade, third party provider for cXML mapping on SAP end

## Slide 24: Project Governance
Status Call Cadence
Resources
Detailed PDF Supplier Guide - Go to: https://support.ariba.com/Item/view/189139
Cadence: Weekly
Search Knowledgebase/Tech Notes – connect.ariba.com
Day/Time:<Day and time>
Required attendees: <Person who have to be present from supplier on the call>
Supplier Information Portal (spec guides, project doc) – Log into your production account and go to Customer Relationships.
Ariba Cloud Statistics – SAP Cloud Service Status | Cloud Availability Center | SAP Trust Center - Detailed information and latest notifications about product issues and planned downtime, if any, during a given day, new releases, and new features

## Slide 25: Transition to Support

## Slide 26: Transition To Support
Post Go-Live Support
Seller Integrators provide 2 weeks support post Go-Live during Live transactions starting with the first transaction in Production.
After the two week period - a Service Request should be created for any request. (Steps detailed in the link here below)
How do I contact SAP Ariba Customer Support as a supplier?

## Slide 27: Thank you.

## Slide 28: Copyright

## Slide 29: Copyright