## Slide 1: Electronic Integration on Ariba Network
Customer
<Seller Name> With <Novartis> Emilia Stefan <Meeting Date>

## Slide 2: Agenda
Introductions – Project Team
Kick Off Meeting Objectives
Presentation Speakers
Seller Integration Methodology
Six steps approach
Project Life Cycle
RACI
Current Status
Project Scope - Challenges : Impacting Timeline
Project Planning & Milestones
Project Timelines
Resourcing & Governance Model
Transition to Support
Notes: The purpose of the Kick Off call is to formally start the integration project with Buyer and Supplier teams, define the project scope, and the targeted completion (Go Live) date.
********************************************
The general objectives for today’s call.
Capture action items from discussions in the Action Items slide at the end of the deck.

## Slide 3: Kick Off Meeting Objectives
Review scope of integration project
Define project plan
Define project timelines
Set project governance.
Transition to Ariba Support.

## Slide 4: Participants
Company | Name | Role | Details
Novartis | Daniel Enache | Project Lead | 
Novartis | Oliver Wait | Testing coordinator | 
Ariba | Emilia Stefan | Seller Integrator | 

## Slide 5: Seller Integration Methodology – Six stage integration
Planning and Testing are the most critical and time consuming steps
Milestone dates to be determined at kick-off meeting
Plan
Design
Build
Test
Deploy
 | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 | 
Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Build |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deploy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Go Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Go Live

## Slide 6
Kick Off Meeting Define Project Scope Documents, business rules, format | Configurations Confirm AN Account (ANID) set up Test account configured Routing configured. | Supplier Development Performs Dev and QA testing of maps | UAT Testing Conduct UAT testing with Customer Pre-defined test scenarios | Migration to Production Seller migrates maps to Production | Production Transactions Confirm successful transactions in Prod
Define Project Plan Agree on milestone dates. | Confirm Relationship established in Test. Define test plan, identify test scenarios | Establish connectivity to the AN | Validate that solution meets requirements | Confirm AN Accounts configured in Production Confirm relationship established in Production | Support ESIM Post-production support
Commit to target Go Live date Define Project Team and Resources Contacts list and governance model. | Supplier’s technical solution defined. | Submit sample cXML/EDI invoices to ESIM for webChecker validation | Formal sign-off and acceptance | Buyer/Seller change management steps Communications, internal set ups | Ongoing technical support Project close
Plan
Design
Build
Test
Deploy
Go Live
Project Life Cycle

## Slide 7: Seller Integration Methodology – RACI

## Slide 8: Current Status (In order to move forward with Planning – asserting where we are!)
Tasks completed to date
  Requirement delivered and reviewed by supplier <Yes/TBD>
  Project contacts have been assigned – <Yes/TBD>
  Relationship accepted - <Yes/TBD>
  PO Flip invoices current in use - <Yes/TBD>
  Ariba Network Accounts Configured - <Yes/TBD>
Notes: Identify any pre-work that may have been accomplished prior to the Kick off.

## Slide 9: Project Scope
Shopping
  What items/services will be purchased?
    Non Catalog Items : <Y/N>
    Catalog Items: <Y/N>
  How are items currently purchased?
    Email: <Y/N>
    Other: <Provide details>
Documents
  The following documents are in scope: [TBD]
    PO: <Y/N>
    INV: <Y/N>
    Optional
    OC (Order confirmation) : <Y/N>
    ASN (Advanced ship Notice) : <Y/N>
Notes: Objection#1. Define Scope
These are fact finding questions to define as-is and to-be solution.

## Slide 10: Project Scope
Document Format/Transmission [TBD]
  What format will be used?
    cXML: <Y/N>
    EDI: <Y/N>
    CSV: <Y/N>
  What transmission protocol? (Nb: Not applicable for CSV)
    HTTPS: <Y/N>
    AS2: <Y/N>
    None: <Only in case of CSV integration>
Locations in scope of the Novartis e-invoicing project :
Please refer to the attached document for VAT codes, BillTo and ShipTo Addresses and AddressIds required by Novartis.
Notes: Review guide.

## Slide 11: Project scope
Purchase Order Types Supported | Purchase Order Types Not Supported
New Pos | Catalog POs
Change/cancel Pos | Blanket POs (BPO’s)
POs with attachments | Service POs
Legacy Orders (Cut-Over Process)
Legacy orders are supported – currently not in place – will not be applied, we are already live with Pos.

## Slide 12: Project scope
Invoice Types Supported | Invoice Types Not Supported
Individual Detail Invoice: applies against single PO referencing line items; line items may be material items. | Invoice against service PO
Partial invoice: Invoice against a portion of the items on a PO. | Non-PO Invoice: invoice against PO not transacted via the Ariba Network
Invoice against material PO | Non-PO invoice against contract or master agreement
lineLevelCreditMemo (cXML 1.2.018 and higher) invoice purpose set to “lineLevelCreditMemo” | Invoice against Blanket PO
Duplicate Invoice: invoice numbers may be reuse in case of reject/fail of original invoice | Header Invoice: single invoice applying to single PO without item details
 | Header Credit Memo
 | Debit Memo
 | Cancel Invoice
 | Invoice against Pcard
 | Invoices with attachment Summary invoices

## Slide 13: Project Scope - additional information
    Please note that the Legal biding document is the one in Ariba !
    Please review the attached document for more details regarding :
- the Digital signature Process in Chapter 4
- Storage and Archiving page 27
    - the types of rules we have and how they are applied pages : 30 – 34. If needed, you may review details about the different validation rules in Chapter 3
Notes: Review guide.

## Slide 14: Challenges : Impacting Timeline
3rd Party Involvement
Number of projects engaged in
Vacation and holiday planning
Buyer and Seller aligned on all test cases for testing phase.
Testing scenarios available to be discussed.

## Slide 15: Timeline Milestones
Phase | Milestone | Owner | Duration | Date Due
Plan | Signoff on Project Plan & Timelines | Supplier | 1 week | 
Design | Buyer specs reviewed | Supplier | 1 week | 
Build | Data mapping completed, webChecker passed | Supplier | 3 weeks | 
Test | Testing completed/Sign off on Test Cases | All | 3 weeks | 
Deploy | Confirm Cutover activities completed | All | 3 days | 
Go Live | Confirm Go Live | All |  | 
Notes: Objective#3 – Define project timelines
Based on definitions of the project phases, enter milestone dates agreed upon by all parties during the Kick Off call.
These should be dates that are realistic and achievable. Discuss dependencies on each task and identify risks and mitigations.
Discuss the possibility of using PO Flip as a bridging strategy.

## Slide 16: Project Governance
Establish Status Call Cadence
  <Weekly> OR <bi-weekly>
  <day>, <time>
  <List of Participants>
  Testing Phase
  <daily>
  <day>, <time>
  <List of Participants>
Resources
  Ariba Implementation Guides - Go to: http://supplier.ariba.com/help
  Supplier Information Portal (spec guides, project doc) – Log into your production account and go to Customer Relationships.
  Search Knowledgebase/Tech Notes – Connect.ariba.com
Notes: Objective #4. Set expectations for project logistics

## Slide 17: Notes and action list
Owner | Action | Original Due Date | ETA/Status
 |  | 10-12-14 | 
Action Items

## Slide 18: Roles & Responsibilities – Project Team
Contact Name | Buyer Role | Responsibility
Daniel Enache | Project Lead | Main contact for project coordination Enforce compliance of project timelines
 | Technical Contact | Support of cXML/EDI Identified Supplier testing Provide connection parameters to ERP systems Assist in troubleshooting document errors from the application/ERP
 | Supplier Enablement Lead / Testing Contact | Generate Test Orders Reconcile and approve invoices Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Supplier Role | Responsibility
 | Project Lead (Contact Name) | Main contact for project coordination Provide commitment to project timeline Understand buyer's transaction validation rules Participate in status meetings
 | Technical (Developer) (Contact Name) | Provide technical details for integration to back-end systems Perform data mapping Assist in troubleshooting document failures
 | Testing Contact (Contact Name) | Generate Test Orders Reconcile and approve invoices Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Ariba Role | Responsibility
Emilia Stefan | Integration Manager | Manage end-to-end supplier integration Troubleshoot failed/rejected documents Ensure timely completion of project milestones Escalate issues to appropriate person/team
 | Customer Support | Support Post-production issues
Notes: This slide will be included in the KO slides for suppliers

## Slide 19: Transition To Support
Post Go-Live Support
ESIMs provide 2 weeks support post Go-Live during Live transactions starting with the first transaction in Production.
After the two week period - a Service Request should be created for any request. (Steps detailed in the next slides)
Direct access to Customer Enablement Experts for onboarding assistance : 1– 800 – 974 – 4899 *
*Suppliers can call this number for non-technical issues.

## Slide 20: Supplier Support Post Go-Live
    Go to http://supplier.ariba.com
Access the Help section from the right corner from your Test / Production account and choose Help Section - Help center

## Slide 21: Supplier Support Post Go-Live
Access the Help section from the right corner from your Test / Production account and choose Help Section - Help center Select option Support center.
Type in a search word and get the needed documentation
Use the Online form or the live chat or contact our customer Support by phone.

## Slide 22: Thank you
 | Emilia Stefan ¦ Seller Integrator – Business Network Integration ¦ Ariba, an SAP Company www.ariba.com ¦ office : 00420 225 372 624