## Slide 1: Electronic Integration on Ariba Network Supplier with Kyndryl
Speaker’s Name, SAP
Month 00, 2023

## Slide 2: Agenda
What is Integration?
Current Status
Project Scope
Project Scope Documents
Seller Integration Methodology
Project Life Cycle
Best Practices
Timeline Milestones
Roles & Responsibilities – Project Team
Challenges: Impacting Timeline
Project Governance
Transition To Support

## Slide 3
What is integration?
PO Flip sellers
Standard Account Seller
Integrated sellers
Customer
Supplier PO Flip
Manual Entry
Supplier
Standard Account
Manual Entry
Supplier Integration
Machine to Machine
Integration

## Slide 4: Current Status/ Scope

## Slide 5
Tasks completed to date
Relationship accepted
Y/N
Location
Country
ANIDs
Buyer - AN11074061242
Ariba Network Accounts Configured
Y/N
Supplier - <AN00..>
Catalog
CIF / Punchout lvl. 1&2
Current Status

## Slide 6
Project Scope
Purchase Orders
Catalog / Non-catalog PO
Service Entry Sheet
Out of scope
OC - Order Confirmation
Optional
ASN - Advance Ship Notice
Invoices
Optional
Out Of Scope
Credit Memo
Out Of Scope
Blanket PO
New PO
Change PO (if applicable)
Catalog / Non-catalog PO
Blanket PO
Cancel PO
How are items currently purchased?
Procurement Solution
Type of Items in Scope
Email/Legacy integration
P2X/POIA
Catalog
Non-catalog
Direct PO (if applicable) – Series 45 (HH) or 52 (AH)
Test Plan:

## Slide 7
Format
cXML
Transmission
cXML - HTTPS
X12 - AS2
D96A
X12 - (NAMER)
D96A - AS2
SAP Ariba Cloud Integration Gateway is solution for integration for cXML
and also for non cXML Customers
    Main Goal: To simplify integration and shorten the integration timeline
    Covering more industry and regional standards
    Providing self testing capabilities
    Please note that the Legal biding document is the one in Ariba!

## Slide 8
Project Scope - Documents
Purchase Order Types Supported | Purchase Order Types Not Supported
Catalogue | Legacy PO
Change PO | P-Card PO
Cancel Order | 
Service PO (Material structure) | 
PO with multiple of UOMs | 
Blanket PO | 
Non-catalogue PO | 
Cancel Pos | 
Standard PO Acting as a Blanket PO | 
Invoice Types Supported | Invoice Types Not Supported
Out Of Scope | Out Of Scope

## Slide 9: Project Planning

## Slide 10: Seller Integration Methodology – Six stage integration according to our best practice
Planning and Testing are the most critical and time consuming steps
Milestone dates to be determined at kick-off meeting
If Invoice/OC in scope, can supplier start with using Ariba portal whilst integration is ongoing?
Plan
Build
Test
Design
Deploy
Go Live

## Slide 11: Seller Integration Methodology – Six stage integration according to our best practice
Planning and Testing are the most critical and time consuming steps
Milestone dates to be determined at kick-off meeting
If Invoice/OC in scope, can supplier start with using Ariba portal whilst integration is ongoing?
Plan
Build
Test
Design
Deploy
Go Live

## Slide 12: Project Life Cycle – Integration
Plan
Build
Test
Design
Deploy
Go Live
Kick Off Meeting Define Project Scope Documents, business rules, format | Configurations Confirm AN Account (ANID) set up Test account configured Routing configured. | Supplier Development Performs Dev and QA testing of maps | UAT Testing Conduct UAT testing with Customer Pre-defined test scenarios | Migration to Production Seller migrates maps to Production | Production Transactions Confirm successful transactions in Prod
Define Project Plan Agree on milestone dates. | Confirm Relationship established in Test. Define test plan, identify test scenarios | Establish connectivity to the AN | Validate that solution meets requirements | Confirm AN Accounts configured in Production Confirm relationship established in Production | Support SI Post-production support
Commit to target Go Live date Define Project Team and Resources Contacts list and governance model. | Supplier’s technical solution defined. | Submit sample cXML/EDI invoices to SI for validation | Formal sign-off and acceptance | Buyer/Seller change management steps Communications, internal set ups | Ongoing technical support Project close

## Slide 13: Best practices for the supplier
Participate on weekly project follow up meetings (30 Minutes) with Supplier Integrator during the whole integration process;
    NB: When catalog in scope, the supplier must agree on a way to monitor the implementation with their CKE (mail, weekly meeting)
Plan
Get familiar with the cXML guideline, define roles and responsibilities of project resources and agree on milestone dates;
Design
Defines the test scenarios; configure the Ariba account in production and in test mode;
Build
Establish connectivity to Ariba network (suppliers already on the network with other buyers will already have connectivity setup), create a cXML sample for the required transaction documents;
Test
Deploy
Go Live
Technical contact is engaged in day to day testing activities: post documents on Ariba test environment according to the test scenario, log on Ariba and check their status, receive technical advices from Supplier Integrator;
NB: when catalog is scope, the catalog needs to be available before testing phase start
Supplier should migrate his account to production mode; internal communication for the switch to production mode is needed;
Document exchange runs in production mode; Supplier integrator provides technical support during the first two weeks;

## Slide 14: Timeline Milestones – will be reviewed and feedback on <Date>
Phase | Milestone | Owner | Duration | Date Due
Plan | Signoff on Project Plan & Timelines | Supplier | 2 weeks | 
Design | Buyer specs reviewed | Supplier | 3 weeks | 
Build | Data mapping completed | Supplier | 4 weeks | 
Catalog deployed | Catalog is deployed in test an available to send POs | All |  | 
Test | Testing completed/Sign off on Test Cases | All | 4 weeks | 
Deploy | Confirm Cutover activities completed | All | 1 week | 
Go Live | Confirm Go Live (week 12) | All |  | 

## Slide 15: Roles & Responsibilities – Project Team Challenges and Governance

## Slide 16
Roles & Responsibilities – Project Team
Contact Name | Supplier Role | Responsibility
 | Project Lead (Operational Lead) | Main contact for project coordination Provide commitment to project timeline Understand buyer's transaction validation rules Participate in status meetings
 | Technical (Developer) | Provide technical details for integration to back-end systems Perform data mapping Assist in troubleshooting document failures Coordinate go live with functional resource
 | Testing Contact | Define & Validate catalogue content with buyer Analyze incoming Orders Generate Test Invoice Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Buyer Role | Responsibility
 | Project Lead (Supplier Enablement lead) | Main contact for project coordination Enforce compliance of project timelines
 | Technical (Developer) | Support of cXML/EDI Identified Supplier testing Provide connection parameters to ERP systems Assist in troubleshooting document errors from the application/ERP
 | Testing Contact | Define & Validate catalogue content with Supplier Generate Test Orders Reconcile and approve invoices Assist in other testing activities, coordinate go-live Download & validate applicable test transactions; load & process through ERP
Contact Name | Ariba Role | Responsibility
 | Seller Integrator | Manage end-to-end supplier integration Troubleshoot failed/rejected documents Ensure timely completion of project milestones Escalate issues to appropriate person/team
 | Supplier Enablement Lead | Consolidate all suppliers enablement status for reporting to MSD
 | Catalogue integrator | Support Setup and testing of Catalogue with buyer and supplier

## Slide 17: Challenges: Impacting Timeline
3rd Party Involvement
Y/N
In case of Y – specify relationship and details
System Maintenance
Dates/ Occurrences
Ex. every Sunday..
Vacation and Holiday Planning
<Supplier-Name of resource: list of holiday dates>
<Buyer-Name of resource: list of holiday dates>
<Ariba-Name of resource: list of holiday dates>

## Slide 18: Project Governance
Status Call Cadence
Resources
Ariba Implementation Guides - Go to: http://supplier.ariba.com/help
Cadence: Weekly
Supplier Information Portal (spec guides, project doc) – Log into your production account and go to Customer Relationships.
Search Knowledgebase/Tech Notes – connect.ariba.com
Ariba Cloud Statistics – http://trust.ariba.com - Detailed information and latest notifications about product issues and planned downtime, if any, during a given day
Ariba Network Notifications – http://netstat.ariba.com - Information about downtime, new releases, and new features
Day/Time:<Day and time>
Required attendees: <Person who have to be present from supplier on the call>

## Slide 19: Transition to Support

## Slide 20: Transition To Support
Post Go-Live Support
Seller Integrators provide 2 weeks support post Go-Live during Live transactions starting with the first transaction in Production.
After the two week period - a Service Request should be created for any request. (Steps detailed in the file attached)

## Slide 21: Thank you.
Contact information:
  F name L name
  Title
  Address
  Phone number